PLAN NH COORDINATING COMMITTEE MEETING NOTES from

Tuesday, October 17, 2017

6:30 pm at the Kensington Public Library

Present: Lynne Monroe, Peter Merrill, Elaine Kaczmarek, Joni Praded, Bob Solomon, Susie Gilbert.

Key topics from last meeting (10/10/17) were revisited and updated.

1.Publicity Efforts.

- We will try to have a reporter at the event if possible.

- Flyer and Trifold. They have been distributed widely. Racks at the Town Hall, Library, Farm, Country Brook, Church, Alnoba, stores in Exeter.

- Kensington Elementary School have distributed the flyers via email and put the event on the signboard in front of the school.

- The Facebook site is up and Susie is adding things. Folks are encouraged to share it on their own pages.

- Webpage on the Town website. Kathy put up the new material and the overall look is better. Check it out! https://www.town.kensington.nh.us/

- Jim Webber made buttons using the art from the children’s mural. Members of the committee will be distributing and wearing to create more awareness of the events.

- Town-wide mailing took place to about 750 names in town.

2.Fundraising Efforts.

- The YouCaring website is up and functioning.  Frank Whittemore is ready to receive checks. Susie will accept checks at the Library. More donations are needed to reach the goal to cover the total expenses.

- Frank Whittemore is making us a spreadsheet to track our expenses and donations.

3.Public Awareness Efforts.

There will be another meeting of the town, department, committee leaders with the Plan NH team, at 1:30 Friday (10/20) at the Grange.

4.Facilities

- We will use the Grange for the sessions on Friday and the Town Hall on Saturday.

- The Grange has tables and chairs and a kitchen. We will need to arrange a circle of chairs for the meeting with town leaders first thing on Friday (10/20). Then we’ll put up the tables for the listening sessions, following the town leaders meeting. A wireless ‘Hotspot’ at the grange will be set up for Internet access, if needed. We will arrange for a microphone (and a podium) with the KES staff.

- We will use the Town Hall for the Saturday activities. It has Internet access and a projector screen (wall). The small kitchen will be enough for team meals. After the work session we will set it up for the final presentation.

- We need the bus to start this brief tour promptly at 11:00 on Friday. The bus will come earlier just in case.

Materials needed by Jen and the Plan NH team are being pulled together from various sources for Friday. Still looking for a volunteer to video the final presentation on Saturday in the Town Hall.

5.Food and Lodging

- Lynne has lots of paper products and a huge coffee urn and will make a large salad.

- We need to arrange rooms for team members from far away. Robin is making a list, so we will have their housing needs shortly.

- Peter is arranging for the FARMSTAND food needs, two lunches for the Plan NH team, final count should be about 10 – 12 people. Lunches will need to be ‘finger ready’ food. We need water in jugs with lemon and coffee service for participants on Friday.

6.The Prescott House

- We want to be sure to have folks tour it on Friday, if they want to. Jen and Robin know this building would be just an open house with flyers to walk through, not an official tour.

- Lynne will make a small handout with the history and facts, with signs in rooms.

7.Children’s Art Project

- The art teacher will do a project using the “Kensington in the Future” historic postcard and ask them to create pictures of how they see the “future” of the town center.

8. Other items

- A press release has been sent out by Susie to the Carriage Town News and Exeter Patch.

- We need to send a special email to Leaders of all groups for the leaders meeting from 1:30 – 3:00 on Friday. Lynne will put together an email to send to the list we had for the previous meeting plus others. Then each of us can tailor it and send it out to everyone we know!

- Weather forecast for both days looks perfect!

List of Plan NH team members, as of 10/17/17, but subject to change:

Peter Michaud, NHDHR

Andrew Cushing, NHPA

C.R. Wilke, NHDOT

Matt Sullivan, planner, Wolfeboro

Sarah Gartska, UNH public policy

Christine McMann, architect

Jen Martel, landscape architect, team leader

Robin Le Blanc, Plan NH director

Final arrangements and schedule for Plan NH Charrette event:

Thursday- Chairs and tables to be arranged at Grange for Friday meetings, etc.

Setup children’s artwork and other photographs (then/now) of nearby buildings.

Final count for lunch arrangements, sandwiches from Farmstand.

Friday- 	Grange

830am Setup food and facility prep by Lynne M., and other team members.

1000-1100 Plan NH team arrives, Bus Tour of ‘Upper/Lower Village’ areas.

Lunch after tour completed

130-300 Town department leaders meeting

330  First Listening Session

530  Potluck Supper

630  Second Listening Session

800  End of Sessions (clean up and prep for move to Town Hall Saturday morning)

Saturday- 	Town Hall (meeting room)

730 Move Plan NH Charrette Team and materials, tables, chairs, etc.

800  Working Session for PlanNH begins

!200 Lunch

300  Plan NH Charrette Final Presentation

500  Clean up Town Hall meeting room (return materials as schedules allow)

Meeting adjourned at 815pm